## Cover Page
Retail Banking System
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
Name
Role
Signature
Date
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog - Instructions MARS: Protected Controlled Copy
Sprint Backlog
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
Sample
The sheet sample is an example sheet on how to fill the sprint backlog. Trainees can refer it to fill the details in the sheets Sprint 1/2/3.
Sprint 1/2/3
| User Story & Task Id | List the User Story id taken from product backlog that are selected to be completed in the particular sprint & List the number of tasks the User story is split into..
| Task | Name the tasks the user story is split into.
| Story Points | Enter the story points that was given for the user story during Sprint planning
| Assigned to | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5 | Task done in Day1/2/3/4/5 - Sprint review and retrospective to be held on Day 5
| Total | Summation of the estimation per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sample
Sprint Backlog <Ratail Banking System> Project ID: MARS Protected Controlled Copy
USER STORY & TASK ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_1 | User Registration | 8
Task_1 | Create table to store Admin details |  | Trainee_2 |  | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Design the registration page |  | Trainee_3 |  | 3 | 1 | 1 | 5 | 0 | 1
Task_3 | Design Login page |  | Trainee_4 |  | 1 | 0.5 | 0 | 3 | 0 | 0
Task_4 | Develop authentication process for login |  | Trainee_1 |  | 0.5 | 1 | 2 | 3 | 1 | 0
US_2 | Admin Home | 1
Task_1 | Create table to store Admin details |  | Trainee_3 |  | 3 | 3 | 0.5 | 0.5 | 0 | 0
Task_2 | Design the Admin registration page |  | Trainee_4 |  | 3 | 5 | 5 | 1 | 1 | 1
Task_3 | Develop code for authentication |  | Trainee_3 |  | 2 | 2 | 5 | 0 | 1 | 0
Task_4 | Develop code to store the admin details |  | Trainee_4 |  | 5 | 5 | 9 | 5 | 1 | 0
US_3 | Listing courses | 5
Task_1 | Develop code for Admin or vendor to add a course |  | Trainee_1 |  | 8 | 6 | 0 | 0 | 0 | 0
Task_2 | Develop Code ofr Admin or vendor to edit a course |  | Trainee_2 |  | 3 | 1 | 3 | 3 | 3 | 0
Task_3 | Develop code for - On clicking on edit a form should be pop up With valid input clicking on Add/update will update the database |  | Trainee_3 |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1
Task_4 | Develop code for Admin or vendor to activate or deactivate a course |  | Trainee_4 |  | 2 | 0.5 | 0 | 0 | 0 | 0
US_4 |  | 8
Task_1 |  |  |  |  | 9 | 4 | 2 | 2 | 1 | 1
Task_2 |  |  |  |  | 6 | 6 | 3 | 3 | 3 | 1
Task_3 |  |  |  |  | 6 | 2 | 8 | 8 | 1 | 0
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
US_5 |  | 3
Task_1 |  |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1
Task_2 |  |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9
Task_3 |  |  |  |  | 9 | 9 | 9 | 4 | 3 | 3
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0
TOTAL |  |  |  |  | 78 | 60 | 59 | 41 | 20 | 18

## Sprint -1
Sprint Backlog <Retail banking System> Project ID: <2767> MARS: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_1 | Role Selection | 3 |  | completed
Task_1 | Design the role selection page |  |  |  | 18.5 | 5 | 4 | 4 | 2 | 3.5
Task_2 | Develop authentication process for login |  |  |  | 19 | 4 | 4 | 5 | 4 | 2
US_2 | User registration and login | 3 |  | completed
Task_1 | Create table to store Employee details |  |  |  | 11 | 2 | 4 | 4 | 2 | 1
Task_2 | Employee Authentication |  |  |  | 24 | 6 | 5 | 4 | 5 | 4
Task_3 | Design Login page |  |  |  | 13.5 | 2 | 3.5 | 2 | 2 | 4
US_3 | User Authentication | 2 |  | completed
Task_1 | Develop authentication process for login |  |  |  | 18 | 3 | 2 | 2 | 6 | 5
Task_2 | Validation |  |  |  | 13 | 2 | 2 | 2 | 3 | 4
Task_3 | Customer Authentication |  |  |  | 8 | 0.5 | 1 | 3.5 | 1 | 2
US_4 | Create Account for Customer | 5 |  | completed
Task_1 | Create table to store Customer details |  |  |  | 10 | 2 | 2 | 2 | 2 | 2
Task_2 | Design the registration page |  |  |  | 12 | 2 | 1.5 | 2 | 1.5 | 3
Task_3 | Validation |  |  |  | 12 | 3 | 3 | 1 | 3 | 2
US_5 | User Account Creation | 5 |  | completed
Task_1 | Create Customer Account |  |  |  | 15 | 3 | 3 | 3 | 3 | 3
Task_2 | Validation |  |  |  | 15 | 4 | 2.5 | 3 | 4 | 1.5
US_6 | View Customer | 13 |  | completed
Task_1 | Display Customer |  |  |  | 11 | 1.5 | 2.5 | 2.5 | 1.5 | 3
TOTAL |  |  |  |  | 200 | 40 | 40 | 40 | 40 | 40

## Sprint -2
Sprint Backlog Retail Banking System Project ID:<2767>. MARS: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_7 | View Customer Details | 13 |  | completed
Task_1 | Display Customer Details |  |  |  | 5 | 1 | 2 | 1 | 0.5 | 0.5
Task_2 | Design the Customer page |  |  |  | 5.5 | 2 | 1 | 1 | 0.5 | 1
Task_3 | Validation |  |  |  | 4 | 1 | 0.5 | 1 | 1 | 0.5
US_8 | Customer Deposit Amount | 8 |  | completed
Task_1 | Coding to make deposit |  |  |  | 5 | 2 | 1 | 1 | 0.5 | 0.5
Task_2 | Design the Deposit requirements |  |  |  | 6 | 1 | 2 | 2 | 0.5 | 0.5
Task_3 | Validation |  |  |  | 6.5 | 1 | 1 | 2 | 1 | 1.5
US_9 | Service Charge Deduction | 13 |  | completed
Task_1 | Coding |  |  |  | 6.5 | 2 | 0.5 | 2 | 1 | 1
Task_2 | Design View Requirements |  |  |  | 10 | 2 | 3 | 2 | 1 | 2
US_10 | User Login | 3 |  | completed
Task_2 | Design the Login page |  |  |  | 8 | 1 | 2 | 2 | 1 | 2
Task_3 | Validation |  |  |  | 8.5 | 1.5 | 1.5 | 1.5 | 2 | 2
US_11 | Withdraw Amount | 5 |  | completed
Task_1 | create table to accept and show withdrawal requiements |  |  |  | 6.5 | 1 | 1.5 | 1 | 2 | 1
Task_2 | Code to Withdraw |  |  |  | 7 | 2 | 1 | 1 | 1 | 2
Task_3 | Validation |  |  |  | 9 | 1.5 | 1.5 | 1.5 | 1.5 | 3
US_12 | Transfer Amount | 8 |  | completed
Task_1 | Table to transfer amount |  |  |  | 5.5 | 0.5 | 1 | 1 | 1.5 | 1.5
Task_2 | Code to transfer amount |  |  |  | 7.5 | 1 | 1.5 | 0.5 | 1.5 | 3
Task_3 | Validation |  |  |  | 7.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
US_13 | Transaction Details | 8 |  | completed
Task_1 | Table the transaction details |  |  |  | 7.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
Task_2 | Design and create transaction details |  |  |  | 9 | 2 | 2 | 2 | 2 | 1
US_14 | Delete Customer | 13 |  | completed
Task_1 | Create table to delete customer |  |  |  | 8 | 2 | 2 | 1 | 2 | 1
Task_2 | Design and layout |  |  |  | 7 | 2 | 1 | 1 | 2 | 1
Task_3 | Validation |  |  |  | 12 | 3 | 2 | 2 | 1 | 3
US_15 | View Deleted Customer Account | 13 |  | completed
Task_1 | View deletedd customer |  |  |  | 9 | 2 | 2 | 2 | 2 | 1
Task_2 | Code to view requirements |  |  |  | 10 | 1 | 0.5 | 1.5 | 4.5 | 3.5
Task_3 | Validation |  |  |  | 7 | 1 | 2 | 1 | 2 | 1
US_16 | Customer/Employee Logout | 5 |  | completed
Task_1 | Logout Coding |  |  |  | 10.5 | 1.5 | 1.5 | 3 | 3 | 1.5
Task_2 | Design and requirements |  |  |  | 12 | 2 | 3 | 3 | 2 | 2
TOTAL |  |  |  |  | 200 | 40 | 40 | 40 | 40 | 40

## Data (hidden)
In-Progress
Completed
N/A